## Work Flow 2020
Customer Name ABC | Address | Phone # | Date Signed | Permit out to TWP Date | Permit # | TWP Name | TWP Phone # | Hole Insp Date | Plumb Insp Date | Elect Inspection Date | Job Detail 30 or 60 amp | T and B Pass/Fail Date | Final Elect Pass/Fail | Final Building Pass Date | Brief Notes
Rich Atieh | 2 Fern Terrace Wayne NJ 07470 | 201-686-7380 | July 5 2019 |  |  | Wayne Twp | 973-694-1800 | [7 empty] | Paul Still Making Changes to Plans
Atlantis Pools DIY | 7945 Red Top Rd Hummelstown PA 17036 | 717-648-7485 | Dec 8 2019 | Customer Handling |  | Hummelstown Twp | 732-927-3069
Raquel Ayala | 37th Street North Arlington NJ 07031 | 201-538-1561 | Jan 25 2019 | Might Cancel |  | North Arlington Twp | 201-538-1561
Jennifer Bondarew | 371 Casino dr Farmingdale NJ 07727 | 908-216-4412 | Nov 11 2019 | Nov 26 2019 |  | Howell Twp | 732-938-4500 | [7 empty] | Sent permit to Customer
Frank Costantini | 5261 West Chester Pike Newtown Sq PA 19073 | 484-368-4818 | Nov 30 2019 |  |  | Williamstown Twp | 610-647-5300 | [7 empty] | Waiting on Survey from Customer
Giuliano Cristino | 51 Wolf Hill dr Warren NJ 07059 | 732-927-3069 | Dec 11 2019 |  |  | Warren Twp | 908-753-8000
Jonathan DeChurch | 37 Leatherwood dr Collegeville Pa 19426 | 267-446-2387 | Nov 4 2019 |  |  | Upper Providence Twp | 610-933-9179 | [7 empty] | Waiting on Survey from Customer
Donna Deghetto | 3 beechnut Street Hillsdale NJ 07642 | 201-230-2985 | Feb 19 2019 | April 1 2019 | 2019-0189 | Hillsdale Twp | 201-666-4800
Diane Dewitt | 349 Dunhams Corner Rd East Brunswick NJ | 908-217-7101 | Dec 5 2019 |  |  | East Brunswick | 732-390-6870 | [7 empty] | Waiting on Topo
Paul Distasio | 5 Renier ct Middletown NJ 07748 | 954-614-7899 | Oct 22 2019 | Jan 3 2020 |  | Middletown Twp | 732-615-2000
James Dobson | 315 W Branch Rd Lincoln University PA 19352 | 302-766-5759 | Oct 1 2019 | Nov 25 2019 | 19-100-R | Lower Oxford twp | 610-932-8150
Sandra Garcia | 488 Grove Street Ridgewood NJ 07450 | 866-944-8939 | June 25 2019 |  |  | Ridgewood Twp | 201-670-5500 | [7 empty] | Waiting on Grading Plans own enginner
Caroline Guarino | 780 Ramapo Valley rd Mahwah NJ 07430 | 973-908-7792 | June 12 2019 | Dec 12 2019 |  | Mahwah Twp | 201-529-5757 | [7 empty] | Sent to Customer 12-7-19 Needed to add things
Frank Kist | 263 Wheatsheaf Lane Langhorne PA 19047 | 215-768-3356 | Oct 15 2019 |  |  | Middletown Twp | 215-750-3800 | [7 empty] | Waiting on Grading Plan from Paul amd Deed
Karl Klige | 931 Meadowlark Dr Lanoka Harbor NJ 08734 | 609-937-8951 | Dec 17 2019 |  |  | Lacey Twp | 609-693-1100
Cynthia Lay | 59 Beech Street Nutley NJ 07110 | 973-868-5893 | Sept 11 2019 | Jan 1 2020 |  | Nutley Twp | 973-284-4951 | [7 empty] | Waiting on Grading Plan from Paul
Daniel Lowe | 96 Golf Court Tea Neck NJ | 646-305-3292 | Jan 2 2020 |  |  | Twp of Tea Neck | 201-837-1600 | [7 empty] | Waiting on Topo
Mike & Rose lynch | 6 Lancaster Dr Marlton NJ 08053 | 856-291-1776 | Aug 6 2019 | Oct 5 2019 |  | Evesham Twp | 856-983-2900
Richard Maduzia | 2241 Claymont Dr Quakertown PA 18951 | 610-533-5155 | Nov 22 2019 |  |  | Richland Twp | 215-536-4066 | [7 empty] | Waiting on Plumbing Permit
Jim Mittenhuber | 704 Newell Ave Manahawkin NJ 08050 | 917-440-7845 | Aug 29 2017 | Sept 13 2017 |  | Stafford Twp | 609-597-1000
Dave Murphy | 64 Gina Lane Elkton Md 21921 | 443-907-8399 | Nov 20 2019 | Dec 2 2019 |  | Elkon Twp | 410-398-0970
Liam Nisenfeld | 416 Oak St Audubon NJ 08106 | 856-655-4909 | Dec 19 2019 |  |  | Audubon Twp | 856-547-0711
John Novak | 3117 Oceanic Dr Toms River NJ 07853 | 201-852-6218 | Nov 15 2019 | Jan 3 2020 |  | Toms River | 732-341-1000 | [7 empty] | Waiting on Topo from Paul and Gas from Homeowner
Vincent O'Donnell | 426 W Oak Ave Wildwood NJ 08260 | 610-389-5866 | Sept 11 2019 | Oct 11 2020 | 2019-0528 | Wildwood Twp | 609-846-2000
Frank o'neill | 1628 Ashton Rd Havertown Pa 19083 | 610-256-9271 | Feb 8 2019 | April 30 2019 |  | Havertown Twp | 610-446-1000
Jacob Persofsky | 110 Carlton Ave Haddon Twp NJ 08108 | 215-530-7600 | Aug 5 2019 |  |  | Haddon Twp | 856-854-1176 | [7 empty] | Waiting on Topo and Plumbing info
Michael Petricko | 16 Park Ave Island Heights NJ 08732 | 201-658-4028 | Dec 27 2019 |  |  | Island Heights Borough | 732-270-6415
Josh Prichard | 40 Cassandra Lane Swedesboro NJ 08085 | 856-298-6768 | Aug 21 2019 | Sept 24 2019 | 19-556 | woolwich Twp | 856-467-2666
Eric & Christine Reed | 309 Chesnut Parkway Wallingford PA 19086 | 610-291-5901 | Nov 13 2019 |  |  | Nether Providence | 610-566-4516 | [7 empty] | Need survey from Customer
Gina Rosenfarb | 218 Valhalla Dr Mantoloking NJ 08738 | 908-377-5872 | Nov 15 2019 |  |  | Brick Twp | 732-262-1041 | [7 empty] | Waiting on Topo from Paul (Dec 23 2019)
Dave Salem | 30 Fox Grape rd Flemmington NJ 08822 | 908-303-3073 | Sept 19 2019 | Nov 22 2019 |  | Raritan Twp | 908-806-6100
Stephen Scharadin | 622 Devonshire Dr Oxford Pa 19363 | 610-633-0948 | Oct 23 12019 |  |  | East Nottingham Twp | 610-932-8494 | [7 empty] | Waiting on Survey from Customer and Plumbing Permit from Customer
Scott Thorpe | 1405 Ashton Rd Havertown PA 19083 | 610-842-5487 | Nov 4 2019 | Jan 3 2019 |  | Haverford Twp | 610-446-1000 | [7 empty] | Waiting on Topo
Ron & Andrea Tornese | 6 Broad acre Dr Mt Laurel NJ 08054 | 609-706-3644 | Nov 5 2019 |  |  | Mt Laurel Twp | 856-234-9686 | [7 empty] | Waiting on Engineer and Fence Permit
Jackie Towns | 11 Lund Ct Piscataway NJ 08854 | 732-310-9852 | Oct 9 2019 | Dec 23 2019 |  | Piscataway Twp | 732-562-2300
Sam & Eboni Walker | 712 Gawain Rd Plymouth Meeting PA 19462 | 267-228-4091 | Sept 16 2019 |  |  | Plymouth Twp | 610-277-4100 | [7 empty] | Waiting on Topo from Paul
Villanova Estates | 5300 Grosvenor Ave Riverdale NY 10463 | 914-842-9206 | June 19 2019 | Customer Handling |  | Riverdale Twp | 914-841-9206
WFM Landscaping | 405 Baltimore Blvd Seagirt NJ 08750 | 973-390-2333 | Sept 19 2019 | Customer Handling |  | Borough of Seagirt | 732-449-9599
James & Jenn Wrisley | 10 Taft Ct Hainesport NJ 08036 | 856-261-2576 | Aug 7 2019 |  |  | Hainesport Twp | 609-267-2730 | [7 empty] | Going through Dep. Could be a while

## Pool Schedule
Week of Jan 15 2020
Customer 1
Customer 2
Customer 3
Customer 4
Customer 5